Here’s a more executive-level deliverable version suitable for Jesse — positioned as a formal operational assessment rather than an internal brainstorming document.

MRH Tanzania

Operational Systems Diagnostic & Odoo Transition Plan

Prepared for: Jesse

Prepared by: THE HUMAN LAB

Confidential Internal Assessment

Executive Summary

Following the completion and review of the MRH Tanzania Operational Systems Diagnostic submissions across Finance, Operations, Legal & Compliance, and Sales & Marketing departments, several recurring structural patterns have emerged requiring operational attention.

The assessment indicates that the organisation is not experiencing a people-capability issue, but rather a systems maturity and operational coordination issue resulting from rapid growth, fragmented communication architecture, and increasing dependency on manual operational processes.

The Tanzania operation currently demonstrates:

- strong willingness from employees to collaborate and improve,

- generally healthy cultural alignment,

- clear role understanding within departments,
while simultaneously revealing:

- approval bottlenecks,

- fragmented communication channels,

- inconsistent interdepartmental visibility,

- reliance on manual tracking systems,

- and delayed operational flow due to centralized dependencies.

The implementation of Odoo therefore represents not only a technology deployment, but a critical organisational infrastructure transition.

If structured correctly, the system will significantly improve:

- operational visibility,

- accountability,

- approval efficiency,

- customer management,

- workflow tracking,

- and leadership scalability.

Key Diagnostic Findings

1. Approval & Decision-Making Bottlenecks

A recurring theme across multiple departments was operational delay caused by:

- waiting for approvals,

- missing information,

- unclear authority pathways,

- and delayed communication between departments.

The organisation currently appears to operate through highly centralized decision-routing structures, creating operational dependency on senior leadership and slowing departmental responsiveness.

This is particularly affecting:

- customer response speed,

- workflow continuity,

- and interdepartmental execution.

2. Communication Infrastructure Requires Standardisation

Current operational communication relies heavily on:

- WhatsApp,

- verbal instruction,

- phone calls,

- meetings,

- and manually managed spreadsheets.

While functional during early-stage growth, this structure creates:

- fragmented accountability,

- inconsistent information tracking,

- duplicated effort,

- and reduced operational transparency.

As organisational complexity increases, these informal systems will become increasingly difficult to manage effectively without centralized process architecture.

3. CRM Absence Is Affecting Sales & Customer Management

The Sales & Marketing division consistently identified the absence of a CRM platform as a significant operational limitation.

Current customer management processes remain partially manual, affecting:

- customer follow-up consistency,

- lead tracking,

- sales reporting,

- and customer relationship continuity.

This creates potential revenue leakage and limits scalability within the commercial operation.

4. Structural Visibility Between Departments Is Partial

Most employees demonstrated general awareness of other departments; however, visibility remains inconsistent and highly dependent on informal communication structures.

This results in:

- delayed coordination,

- duplicated processes,

- workflow overlap,

- and dependency on real-time clarification.

The organisation would benefit from more formalized cross-department operational visibility mechanisms.

5. Organisational Culture Remains Stable

Importantly, the diagnostics did not reveal signs of severe cultural instability or employee disengagement.

Employees generally demonstrated:

- professionalism,

- cooperation,

- willingness to improve systems,

- and positive alignment toward organisational development.

This indicates that MRH is intervening at an advantageous stage before operational strain becomes embedded into company culture.

Operational Risk Areas Identified

Immediate Risk Areas

- Approval delays

- Manual customer tracking

- Informal operational communication

- Dependency on individual decision-makers

- Lack of centralized workflow tracking

- Repetitive manual administrative processes

Odoo Transition Plan (90-Day Operational POA)

Phase 1 — Governance & Structural Mapping

Timeline: Weeks 1–2

Objectives

- Define approval authorities

- Clarify escalation pathways

- Map departmental ownership structures

- Standardize reporting lines

- Identify duplicated workflows before automation

Key Deliverables

- Operational authority matrix

- Departmental workflow maps

- Approval hierarchy framework

- Role accountability definitions

Phase 2 — Core Odoo Deployment

Timeline: Weeks 2–5

Priority Modules

CRM Deployment

To centralize:

- lead management,

- customer follow-ups,

- sales tracking,

- and customer communication history.

Approval Workflow Integration

To:

- reduce approval latency,

- improve visibility,

- and establish accountability tracking.

Task & Workflow Coordination

To:

- centralize operational assignments,

- monitor progress,

- and reduce dependency on verbal instruction.

Finance & Compliance Integration

To improve:

- reporting structure,

- document traceability,

- supplier tracking,

- and audit readiness.

Phase 3 — Communication Restructuring

Timeline: Weeks 4–6

Objectives

Transition operational communication away from:

- fragmented WhatsApp coordination,

- verbal-only instruction,

- and isolated spreadsheet tracking.

Recommended Structure

WhatsApp Usage Limited To:

- urgent escalation,

- notifications,

- and non-critical coordination.

Operational Actions To Be Managed Inside Odoo:

- approvals,

- task assignment,

- reporting,

- customer tracking,

- and process monitoring.

Phase 4 — Bottleneck Reduction & Delegated Authority

Timeline: Weeks 5–8

Objectives

Reduce operational dependency on centralized executive approvals by:

- delegating routine authority,

- defining approval thresholds,

- and empowering department-level execution.

Expected Outcome

- faster operational flow,

- reduced leadership congestion,

- improved departmental responsiveness,

- and stronger accountability ownership.

Phase 5 — Performance Visibility & KPI Tracking

Timeline: Weeks 7–10

Recommended KPI Categories

Sales

- lead response time,

- conversion tracking,

- customer follow-up completion.

Operations

- workflow turnaround time,

- supplier coordination efficiency,

- approval speed.

Finance

- invoice processing time,

- reconciliation accuracy,

- overdue approval monitoring.

Legal & Compliance

- regulatory submission timelines,

- document turnaround,

- renewal compliance tracking.

Strategic Recommendation

The diagnostics strongly indicate that MRH Tanzania should prioritize operational systems maturity before further scaling complexity.

The Odoo implementation should therefore be treated as:

an operational restructuring initiative supported by technology,
rather than purely a software deployment project.

Success will depend less on the platform itself, and more on:

- governance clarity,

- adoption discipline,

- delegated operational authority,

- and standardized communication architecture.

Final Assessment

The Tanzania operation remains structurally recoverable and culturally stable.

The workforce demonstrates:

- engagement,

- adaptability,

- and willingness to improve.

The primary weaknesses identified are systemic rather than personnel-based.

With proper implementation discipline, the current Odoo transition presents a strong opportunity to:

- stabilize operations,

- improve scalability,

- increase accountability,

- and build a more resilient organizational infrastructure for future growth.