## Weekly Governance Report
MRH WEEKLY GOVERNANCE & OPERATIONS REPORT
#VALUE! |  | Department / Division | Legal & Compliance
|  | Country / Entity | Tanzania
|  | Reporting Manager | Mary Lamwai
|  | Reporting Period | 11 - 15 May 2026
|  | Date Submitted | 2026-05-15
Fields marked ▼ contain dropdown selections
1. Executive Summary
1. Follow-ups regarding Puma Harvest honey exportation |  | Needs Attention
2. CMA Case Hussein Shio Vs PUMA Harvest which was fixed on 14/05/2026 at Singida |  | Needs Attention
3. Transfer of shares from Citadel Tanzania Limited to MRH |  | Needs Attention
4. Newly court case instituted in Primary Court Singida |  | Needs Attention
5. Preparation of Bellatrix Media Limited Influencer Agreement
2. Key Activities Completed This Week
Influencer Agreement prepared
3. Current Priorities / In Progress |  |  | Overall Status ▼
Attending the Court cases at Singida |  |  | H
Honey exportation permits for Puma Harvest |  |  | H
Transfer of shares from Citadel Tanzania Limited to MRH |  |  | H
4. Operational Challenges / Bottlenecks
Complications in execution of transfer of shares as Citadel Tanzania Limited is not coparating with MRH despite the efforts employed.
5. Decisions / Approvals Required | Context | Recommended Action | Deadline
Decision Required
Travel Form Approval | Attendance of Court cases at Singida | Approved on 14/05/2026 | 16-05-2026
Requiring approval on payment for processing and packaging training of Honey exportation offered by SIDO on behalf of Puma Harvest |  |  | 24-05-2026, and 1-06-2026
6. Financial / Procurement Matters | Overall Status ▼ | Issue / Concern | Support Required
Item
170,000/=Tsh | In Progress | Travel to Singida to attend court cases | Financial assistance
200,000/=Tsh | In Progress | Training on food processing at SIDO in compliance of honey exportation
100,000/=Tsh | In Progress | Training on branding and packaging at SIDO in compliance of honey exportation
7. Risks / Concerns | Overall Impact▼ | Mitigation / Action
Risk
Failure to attend training offered by SIDO the company shall not be able to obtain export permits | H | no mitigation
Failure to attend court case at Singida will lead us not to be updated with effective court proceedings | H | no mitigation
8. Next Week Priorities
Court cases at Singida
Renewal of MRH Licence
9. Governance & Compliance Check
☐ All approvals properly documented
☐ Financial activity routed correctly
☐ No critical approvals conducted verbally only
☐ Key operational issues reported
☐ Tasks assigned to responsible owners
☐ Supporting documents properly stored
10. Additional Notes
COO Review Section (Internal Use)
Observations:
Required Actions:
Follow-Ups: